## Gantt chart1
Gantt Chart for Building/Installation of Tire Shredder
Task | Start Date | End Date | Duration (Days)
Clearing Field | 2022-01-01 | 2022-01-04 | 3
Gather/Submit Specifications | 2022-01-01 | 2022-01-15 | 14
Facility Construction | 2022-01-04 | 2022-02-03 | 30
Construction Shredder Components | 2022-01-15 | 2022-02-05 | 21
Inspection of Warehouse | 2022-02-03 | 2022-02-12 | 9
Delivery of Shredder Components | 2022-02-05 | 2022-02-12 | 7
Inspection of Components | 2022-02-12 | 2022-02-15 | 3
Installation of Shredder Components | 2022-02-15 | 2022-03-17 | 30
Calibrating | 2022-03-17 | 2022-03-20 | 3
Final Testing | 2022-03-20 | 2022-03-21 | 1
Formulas:
End Date = [Start Date]+3

## Gantt chart2
Task | Start Date | End Date | Duration
Task 1 | 2014-04-01 | 2014-05-31 | 60
Task 2 | 2014-06-01 | 2014-08-05 | 65
Task 3 | 2014-08-06 | 2014-08-28 | 22
Task 4 | 2014-08-29 | 2014-10-14 | 46
Task 5 | 2014-10-15 | 2014-10-26 | 11
Task 6 | 2014-10-27 | 2014-12-06 | 40
1899-12-31
Formulas:
End Date = [Start Date]+60
Start Date = [End Date, row above]+1